## Risk Lists
Top Project Risks as of 09/16/2013
Rank |  | Risk Description | Risk Mitigation Action Items | No. of Weeks Active
This Week | Last Week
1 | N/A | Security Risks - An unsecure platform might be exploited or easily manipulated (e.g. people finding loopholes to avoid fees), which can result in the LA Metro losing profits. | Our group’s architect will develop a cryptosystem for our application that will be tested until it meets the client’s requirements and security standards. | 1
2 | N/A | Partnership Risks - The LA Metro might not be willing to implement our system or work with our group to test our platform on their systems/hardware. | Our project manager is currently in talks with the LA Metro authorities, but we could also potentially do a proof of concept using similar hardware/systems. | 1
3 | N/A | Technical Risks - A technical malfunction of our platform might cause boarding delays for passengers and cause inefficiencies in LA Metro operations. | A back-up system will be designed in a later stage of the project. Also, we will advise passengers who are particularly sensitive to delays to have a back-up physical tap card. | 1
4 | N/A | End-User Risks - End users (passengers) might not have smartphones that have the technical capabilities to support our platform. | A feasibility study will be conducted to verify compatible phone penetration rates, and if needed, we can tailor our platform to target only a certain segment of the customer base that has access to the required technology. | 1
5 | N/A | Timing and Unexpected Risks - To get the application fully working and integrated into the LA Metro system, there will be a large set of evolving requirements. Two semesters might not be enough time to complete the project, especially if there are unexpected risks (e.g. another developer completes the same project before we do, bureaucratic risks, etc.) | We will develop a running list of unexpected risks as they come up and develop strategies to approach them. For example, we would explicitly ask LA Metro for their timeline and ask for an exclusive partnership. | 1
6 | N/A | Dynamic Risks - After the platform has been implemented and integrated, the LA Metro requirements might change, or the technologies being used in relevant processes might change. | If we are under a contract/agreement, the team will develop updates/patches that will adapt to new requirements. Otherwise, we will give the LA Metro a copy of our comprehensive documentation for the software so that necessary changes can be handled in-house. | 1
7
8
9
10